## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Project Brief
| Table 1 | Project Brief
Compliance Calendar
| Table 1 | Compliance Calendar
Budget & Expenditure
| Table 1 | Budget & Expenditure
Reimbursement Tracker
| Table 1 | Reimbursement Tracker
Change Order & Scope Log
| Table 1 | Change Order & Scope Log
Closeout Documentation Index
| Table 1 | Closeout Documentation Index
Continued Use Compliance
| Table 1 | Continued Use Compliance

## Project Brief
Tribal CCIF Compliance Workbook
Purpose | Central workbook for project compliance planning, monitoring, documentation, and closeout.
How to use | Complete blue cells, update tracking tabs regularly, and retain source documentation in the linked folder location.
Project Overview
Project Name |  |  |  | Tribe / Department
Grant Award Number |  |  |  | Project Type
Project Location |  |  |  | Total Project Budget
CCIF Funding Amount |  |  |  | Additional Funding Sources
Contract Execution Date |  |  |  | Estimated Completion Date
Document Storage Location |  |  |  | State Contact
Executed Contract Storage Location |  |  |  | Authorized Signatory
Key Contacts
Role | Name | Department | Email / Phone
Project Lead
Finance Lead
Procurement Lead
Construction Lead
Program Lead
Backup Contact
Compliance Snapshot
Requirement | Responsible Staff | Due / Review Date | Status
Procurement documentation
Reimbursement documentation
Reporting deadlines
Change order approvals
Closeout documentation
Continued use monitoring
Project Summary / Key Risks
Use this space for a concise leadership summary, major milestones, and top compliance or implementation risks.

## Compliance Calendar
Compliance Calendar
Requirement / Milestone | Responsible Staff | Start Date | Due Date | Status | Notes
Examples below |  | mm/dd/yyyy | mm/dd/yyyy |  | Examples below
Q1 Reporting | Grant Manager/Grant Adminstrator | 2026-01-01 | 2026-04-15 | In Progress | Grant recipients must submit progress reports each quarter during the project period.
Q2 Reporting | Grant Manager/Grant Adminstrator | 2026-04-01 | 2026-07-15 | Not Started | Grant recipients must submit progress reports each quarter during the project period.
Q3 Reporting | Grant Manager/Grant Adminstrator | 2026-07-01 | 2026-10-15 | Not Started | Grant recipients must submit progress reports each quarter during the project period.
Q4 Reporting | Grant Manager/Grant Adminstrator | 2026-10-01 | 2027-01-15 | Not Started | Grant recipients must submit progress reports each quarter during the project period.
Reimbursement Submission | Finance Staff | 2026-04-01 | TBD | In Progress | Recipients will be required to submit a disbursement request to Business Oregon, along with documentation of the costs incurred. Recipients may receive advance payments upon request by providing a copy of a signed contract with a contractor licensed by the Oregon Construction Contractors Board.
Facility Photo Submission | Tribal Adminstrator | 2026-04-01 | TBD | Accepted/Approved | Recipients will be asked to submit “before” photos of the project site at their facility at the time of contract execution.

## Budget & Expenditure
Budget & Expenditure Worksheet
Budget Category | Invoice # | Approved Amount | Spent to Date | Remaining | Source | Notes

## Reimbursement Tracker
Reimbursement Tracker
OBDD Funds (Enter Whole Dollars Only) |  |  |  |  | Other / Matching Funds (Enter Whole Dollars Only)
(A) | (B) | (C) | (D) | (E)= [B-C-D] | (F) | (G) | (H) | (I) = [F-G-H] | (J) = [C+D+G+H]
Activity | Approved Budget | Prior Disbursements | Current Request | Balance | Approved Budget | Prior Expenditures | Current Expenditure | Balance | Disbursed & Expended
|  |  |  | 0 |  |  |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Change Order & Scope Log
Change Order & Scope Log
Change Description | Reason | Budget Impact | Approval Status | Approval Date | State Notified? | Documentation Location | Risk Level | Notes
Timeline Extension | Construction delays due to winter weather and supply chain delays for HVAC materials. | No budget increase requested. Costs remain within approved grant budget. | Approved | 2026-04-01 | Yes | Ex: Shared Drive Link | Moderate

## Closeout Documentation Index
Closeout Documentation Index
Document | Document Category | Document Description | Responsible Staff | Status | Due Date | Notes
Project Completion Photos | Program/Project | Up to 5 photographs of the completed renovation showing work quality and completion | Project Manager | Submitted | 2026-09-30 | Photos uploaded to Shared Drive > Grants > ELC Renovation > Closeout Photos. Project completed.
Final reimbursement request | Financial/Expenditure
Final expenditure summary | Financial/Expenditure
Receipts for all grant-related expenses | Financial/Expenditure
Final project narrative | Program/Project
Procurement documentation | Construction/Renovation/Facilities
Continued use documentation | Compliance/Miscellaneous
Certificate of Substaintial Completion or Occupancy (if applicable) | Compliance/Miscellaneous
Licensing approval / Occupancy | Compliance/Miscellaneous

## Continued Use Compliance
Continued Use Compliance Worksheet
Requirement | Documentation Location | Responsible Staff | Review Frequency | Status | Last Review Date | Notes
Maintain open child care services at funded site | Ex: Shared Drive Link | Project Manager |  | Submitted
Comply with continued use period based on award amount
Ensure property owner approval (if leasing)
Document lease or property agreement
Track project completion date
Maintain evidence of service provision
Enrollment/capacity tracking